## Slide 1: Mission Hall Updates
Ask & Learn
Christine Shaff UCSF Real Estate

## Slide 2: Acoustical Improvements
Ceiling above open workstation areas
  Completed on floors 4-7
  Scheduled to finish on 3rd floor this Friday (Sept. 21)
  Scheduled for 2nd floor Oct. 2-5
  Minor follow up expected

## Slide 3: Acoustical Improvements
Focus Room doors
  Completed on floors 4-7
  Underway on 3rd floor
  Scheduled to start on 2nd floor doors next week (Sept. 24)
  Overall completion week of Oct. 1

## Slide 4: Acoustical Improvements
Town Centers
  Select walls
  Expect start early October
  Sequence will be floor by floor, starting on 7 and moving down
  No preparation by occupants needed

## Slide 5: Focus Room Conversions
353 Focus Rooms will have work, 241 (65%) of these will be converted to private offices
Work is scheduled to start on 7th floor Monday Sept. 24, new furniture to be installed Friday Sept. 28
Next set of rooms scheduled Oct. 1-5
Focus Rooms converted each week will be a collection from throughout the building, so no floor will be without available Focus Rooms during the project
Conversion project expected to take 6-8 weeks
All existing furniture and any other items will be removed prior to construction

## Slide 6: Other Mission Bay Construction
UCSF
  Solar installation at Mission Hall
  Weill Neurosciences Building, underground utilities
  PCMB and Center for Vision Neuroscience
  Electric shuttle lot opening Friday
  New parking lot at Block 18, 5th St. connected
Non-UCSF construction
  Muni stop at MB goes away starting Nov. 12 through April 2019
  SFMTA closing 3rd/16th last weekend in November
  Chase Center opens September 2019

## Slide 7: Space Allocation
Letter to Building Governance Committee August 17
  Now posted on Mission Hall website
Meetings with units expected to start in early October